## BP2026_Archive (21Apr26)
Team bucket | New Team bucket | New MCR ID | WBS | Task name | Resource group | Orga new | Cost type | Person booking | BP26 FTE (%) - input | Target Responsible | CF02 FTE(%) - input | Total Hrs 2026 | Rate 2026 | Personnel costs | C-Hub PF | C-Hub Cust Ext | CF02 C-Hub PF | CF02 C-Hub Cust Ext | CF05 C-Hub PF | CF05 C-Hub Cust Ext | Comments | Act Jan-25 | Act Feb-25 | Act Mar-25 | Act Apr-25 | Act May-25 | Act Jun-25 | Act Jul-25 | Act Aug-25 | Act Sep-25 | Act Oct-25 | Act Nov-25 | Act Dec-25 | YTD Actuals 2025 | BAC (CF05 Plan) | EAC (based on YTD actuals) | Gap | Column1
Refunding | Refunding | BM-00110021_003 | BM-00110021_003_00000006 | Refunding for C-Hub main project ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding |  | Refunding | (blank) | [6 empty] | -330000 | 0 | -330000 |  | -330000 | [14 empty] | #REF! | -330000 | -330000 | 0
Stretch target | Stretch target | BM-00110021_002 |  | Stretch target (budget cut) | PS-SC/PAC Other Costs |  | Stretch target | [9 empty] | -400000 |  | -400000 |  | Budget cut = 400k€, set initially on 27-Jan-26 in _003 | [12 empty] | #REF! | -400000 | 0 | 400000
Refunding | Refunding | BM-00110021_005 |  | Refunding for C-Hub XC ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding |  | Refunding | (blank) | [6 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
Customer specific effort |  | BM-00110021_002 |  | Customer integrations | PS-SC/PAC Other Costs | PA-CS | Other cost | assumtption: 10 customer á 80k€ | [6 empty] | 0 | 250000 | 0 | 250000 | 0 | 250000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000005 | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | Other cost | Dirk needed for tranfer to PS | 100% | [5 empty] | 202500 | 67500 | 210000 | 67500 | 210000 | 67500 | PO #0087207184, C-Hub Content & Consultation Q1-Q3 2026 |  | 21953.85 | 22181.16 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 |  |  |  | #REF! | 210000 | 184135.01 | -25864.99
Cojali Development |  | BM-00110021_002 |  | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | Manually added cost | [13 empty] | For Actual only, do not plan in MCR | 21953.85 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Cojali Development |  | BM-00110021_002 |  | RM+RD config + Cojali + Pantaris configs | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | NN | 100% | Alkis | 100% | #REF! | #REF! | #REF! | 78598.6667 | 0 | #REF! |  | 78598.6667 |  | tbd w/ Alin: who is staffed here |  |  |  | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | #REF! | 78598.6667 | 58949 | -19649.6667
Cojali Development | Service Delivery OPS & Support | BM-00110021_002 |  | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | Personnel cost | Dhingra, Manish | 100% | Ann/Alexander | 100% | #REF! | #REF! | #REF! | 52462.84 | 0 | #REF! |  | 52462.84 |  |  | 4166.1956 | 4107.1233 | 4146.7853 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | #REF! | 52462.84 | 51767.2342 | -695.6058
E2E C-Hub System Team |  | BM-00110021_002 |  | Data / rev. Eng. and AI | PS-SC/PAC Other Costs | PA-CS | Other cost | (blank) | other cost | [5 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
Other costs |  | BM-00110021_002 |  | Series Logistics Concept | PS-SC/PAC Other Costs | M | Other cost | (blank) | other cost | [5 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
NA Activities | NA ENG Team | BM-00110021_002 |  | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | Personnel cost |  | 400% |  | 200% | #REF! | #REF! | #REF! | 423141.913 | 423141.913 | #REF! | 423141.913 | 423141.913 | 423141.913 |  |  |  |  | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | 35261.8261 | #REF! | 423141.913 | 423141.9275 | 0.014493
NA Activities | NA ENG Team | BM-00110021_002 |  | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | Manually added cost | [14 empty] | 35261.8333 | 35261.8333 | 35261.8261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 |  | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000008 | VCS SW maintance | PS-SC/PAC Other Costs | VCS | Other cost | (blank) | Walter/Rainer klärt mit Daniel | [5 empty] | 370000 | 0 | 370000 |  | 370000 |  | 27-Feb: Lates planning = 222 kEUR |  |  | 37000 | 18500 | 18500 | 18500 | 18500 | 18500 | 18500 | 18500 | 18500 | 18500 | #REF! | 370000 | 222000 | -148000
Cojali Development |  | BM-00110021_002 |  | VCS SW maintance | PS-SC/PAC Other Costs | VCS | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_003 |  | System integration and performing V&V | PS-SC/XPS PS-SC XPS development | PA-CS | Personnel cost | Weiss Patrick (PS-SC/XPS) | 100% | Alkis | 50% | #REF! | #REF! | #REF! | 124588.8 | 0 | #REF! |  | 124588.8 | [5 empty] | 10382.4 | 10382.4 | 10382.4 | 10382.4 | 10382.4 | 10382.4 | 10382.4 | 10382.4 | 10382.4 | #REF! | 124588.8 | 93441.6 | -31147.2
PjM, Biz Dev, service mng | Service Delivery OPS & Support | BM-00110021_002 |  | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | Sorina (support) + Bianca + Maria (200%) | 200% | Ann | 150% | #REF! | #REF! | #REF! | 117898 | 78598.6667 | #REF! | #REF! | 117898 | 78598.6667 | tbd w/ Alin: is that working out | 6137.136 | 14303.6531 | 6939.0464 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | 9824.8333 | #REF! | 117898 | 115803.3355 | -2094.6645
PjM, Biz Dev, service mng | Service Delivery OPS & Support | BM-00110021_002 |  | Service Management | PS-SC/ETX | Cluj | Personnel cost | Lausch, Ann Kathrin / Cluj PS-SC/ETX | 100% | Rainer | 100% | #REF! | #REF! | #REF! | 81435.7843 | 0 | #REF! |  | 81435.7843 |  |  | 7684.7616 | 8165.8915 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | 6786.3154 | #REF! | 81435.7843 | 83713.8067 | 2278.0224
OPS Team EU (VI) |  | BM-00110021_002 | BM-00110021_002_00000009 | Service Operation EU - VI | PS-SC/PAC Other Costs | Operation | Other cost? |  | to be aligned with Gernot | [5 empty] | 50000 | 75000 | 25000 | 100000 | 25000 | 100000 |  |  |  |  | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | #REF! | 25000 | 18750 | -6250
OPS Team NA (VI) |  | BM-00110021_002 | BM-00110021_002_00000010 | Service Operation NA - VI | PS-SC/PAC Other Costs | Operation | Other cost? |  | to be aligned with Gernot | [5 empty] | 50000 | 75000 | 25000 | 100000 | 25000 | 100000 |  |  |  |  | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | 2083.3333 | #REF! | 25000 | 18750 | -6250
PjM, Biz Dev, service mng | Partner Management | BM-00110021_003 |  | Partner Manager | PS-SC/PAC PAC1 | PA-CS | Personnel cost | Hornung, Floyd? | 100% |  | 20% | #REF! | #REF! | #REF! | 42144.3 | 63216.45 | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
PjM, Biz Dev, service mng | Partner Management | BM-00110021_002 |  | Partner Manager | PS-SC/ETX | Cluj | Personnel cost | Ciolte Natalia Liliana (PS-SC/ETX1) |  | Rainer | 50% | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 40717.8922 | 40717.8922 |  | 3201.984 | 4056.2598 | 4590.4461 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | 3393.1577 | #REF! | 40717.8922 | 42387.109 | 1669.2169
Cojali Development | Supporting Functions | BM-00110021_002 |  | EPQ | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | Personnel cost | Lakshmi, Ramakrishnan | 35% |  | 50% | #REF! | #REF! | #REF! | 18361.994 | 0 | #REF! |  | 26231.42 |  |  | 1602.3829 | 1842.9399 | 1860.737 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | 2185.9517 | #REF! | 26231.42 | 24979.6249 | -1251.7951
Cojali Development | Supporting Functions | BM-00110021_002 |  | Security Manager | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | IN | Personnel cost | Covasa Szilard Fineas (PS-SC/EDS1) | 25% | Lakshmi | 25% | #REF! | #REF! | #REF! | 19649.6667 | 0 | #REF! |  | 19649.6667 |  |  | 1387.5264 | 7472.0576 | 5871.5008 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | 1637.4722 | #REF! | 19649.6667 | 29468.3348 | 9818.6681
Cojali Development | Supporting Functions | BM-00110021_002 |  | Support BGSW (Arun) | MS/END-IN_iGPM Mechanical_Design_Services_W/O_CAD_SW_PS_Sensors | IN | Personnel cost | Palanisamy, Babu | 50% |  | 50% | #REF! | #REF! | #REF! | 19721.52 | 0 | #REF! |  | 19721.52 |  |  | 1574.6042 | 1552.2779 | 1567.2681 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | 1643.46 | #REF! | 19721.52 | 19485.2903 | -236.2297
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_002 | BM-00110021_002_00000011 | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | BD | Other cost | Marianne | same as 2025 | [5 empty] | 87000 | 0 | 87000 |  | 0 |  | CF05: BD costs aggregated to BM-00110021_002_00000012 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_002 |  | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | BD | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_003 |  | Product development lead | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | Personnel cost | Hodzic, Alkis -> Transfer Alkis to PS-S -> C reduces costs | 100% |  | 100% | #REF! | #REF! | #REF! | 226865.1 | 0 | #REF! |  | 226865.1 |  |  | 14975.622 | 23139.679 | 21045 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | 18905.425 | #REF! | 226865.1 | 229309.126 | 2444.026
PjM, Biz Dev, service mng |  | BM-00110021_002 | BM-00110021_002_00000012 | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | BD | Other cost | Rainer, Stan | other cost | [5 empty] | 355125 | 0 | 355125 |  | 578153.672 |  | CF05: BD costs aggregated to BM-00110021_002_00000012 |  |  | 183000 | 48179.4727 | 48179.4727 | 48179.4727 | 48179.4727 | 48179.4727 | 48179.4727 | 48179.4727 | 48179.4727 | 9717.4727 | #REF! | 578153.672 | 578153.254 | -0.418
PjM, Biz Dev, service mng |  | BM-00110021_002 |  | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | BD | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
XC-CP | HW & BSW | BM-00110021_004 |  | C-Hub XC Series Care_004 | Various XC | XC | Other cost | Multiple | [6 empty] | 940241.92 | 0 | 1052369.3155 |  | 1095000 |  | CF05: ~ 43k€ increase (from 1052 to 1095 k€), input Can Oezcan | 51609.3723 | 52372.8221 | 50179.8354 | 91250 | 91250 | 91250 | 91250 | 91250 | 91250 | 91250 | 91250 | 91250 | #REF! | 1095000 | 975412.0298 | -119587.9702
XC-CP | HW & BSW | BM-00110021_005 |  | C-Hub XC Series Care_005 | Various XC | XC | Other cost | Multiple | [6 empty] | 711127 | 0 | 597620.6542 |  | 611000 |  | CF05: ~13 k€ increase (from 598 to 611 k€), input Can Oezcan | 35381.8313 | 39735.227 | 36237.2125 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | 50916.6667 | #REF! | 611000 | 569604.2708 | -41395.7292
XC-CP | HW & BSW | BM-00110021_004 |  | C-Hub XC New Features | Various XC | XC | Other cost | Multiple | [6 empty] | 0 | 286993.92 | 0 | 286994 | 0 | 343003.9503 | CF05: Increased due to XC Stretch target increase |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
XC-CP | HW & BSW | BM-00110021_005 |  | C-Hub XC New Features | Various XC | XC | Other cost | Multiple | [6 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000013 | CVIT Partner Manager | PS-SC/PAC Other Costs | Bari | Other cost | (blank) | 100% | [5 empty] | 98689.3394 |  | 98689.3394 |  | 98689.3394 | [5 empty] | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | 8224.1116 | #REF! | 98689.3394 | 98689.3394 | 0
Cojali Development |  | BM-00110021_002 |  | CVIT Partner Manager | PS-SC/PAC Other Costs |  | Manually added cost | [13 empty] | For Actual only, do not plan in MCR | 8224.1116 | 8224.1116 | 8224.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 |  | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000014 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | Other cost | (blank) | [6 empty] | 80000 | 70000 | 150000 | 113000 | 150000 | 113000 | Cojali Series Integration: PO 0087209779-Q1; PO 0087211879-Q2 |  | 71813 | 68872 | [9 empty] | #REF! | 150000 | 277605 | 127605 | fa
Cojali Development |  | BM-00110021_002 |  | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 9315 | 42535 | 42535 | 42535 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000015 | R&D at Cojali | PS-SC/PAC Other Costs | Operation | Other cost | (blank) | other cost | [5 empty] | 90000 | 270000 | 60000 | 300000 | 60000 | 300000 |  |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | #REF! | 60000 | 50000 | -10000
Cojali Development | Premium Multi-Brand Data | BM-00110021_002 | BM-00110021_002_00000016 | PO for Cojali | PS-SC/PAC Other Costs | VCS | Other cost | Scholz, Sebastian |  | Target resp. |  |  |  |  | 180000 | 0 | 180000 |  | 180000 |  | 27-Feb: Latest plqnning = 332 kEUR |  |  | 130750 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | 22361.1111 | #REF! | 180000 | 332000 | 152000
Cojali Development | Premium Multi-Brand Data | BM-00110021_002 |  | PO for Cojali | PS-SC/PAC Other Costs | VCS | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
Cojali Development |  | BM-00110021_002 | BM-00110021_002_00000017 | VCS R&D | PS-SC/PAC Other Costs | VCS | Other cost | (blank) | [6 empty] | 682500 | 292500 | 682500 | 292500 | 682500 | 292500 | 27-Feb: Latest plqnning = 824 kEUR |  |  | 155105 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | 74321.6667 | #REF! | 682500 | 824000 | 141500
Cojali Development |  | BM-00110021_002 |  | VCS R&D | PS-SC/PAC Other Costs | VCS | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
XC-CP | HW & BSW | BM-00110021_004 |  | C-Hub XC - HW Change for RS-232, K-LINE |  | XC | [8 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
XC-CP | HW & BSW | BM-00110021_005 |  | C-Hub XC - HW Change for RS-232, K-LINE |  | XC | [8 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
Cojali Development | Container App Development | BM-00110021_002 | BM-00110021_002_00000018 | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | BD | Other cost | Gibayev Oleg | 100% | Alki |  |  |  |  | 136028.672 | 0 | 136028.672 |  | 0 |  | CF05: BD costs aggregated to BM-00110021_002_00000012 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
Cojali Development | Container App Development | BM-00110021_002 |  | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | BD | Manually added cost | [13 empty] | For Actual only, do not plan in MCR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
E2E C-Hub System Team | Container App Development | BM-00110021_002 |  | CDK development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | Birnescu Florin (PS-SC/EDS1) | 100% | Alkis | 100% | #REF! | #REF! | #REF! | 78598.6667 | 0 | #REF! |  | 78598.6667 |  |  | 1707.7248 | 3415.7978 | 2775.6186 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | #REF! | 78598.6667 | 66848.1411 | -11750.5255
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_002 |  | Technical Docu Cluj | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | Mindrean Denisa (PS-SC/EDS) --> booking is done by Alin Pantea on her behalf | 50% | Alkis | 50% | #REF! | #REF! | #REF! | 39299.3333 | 0 | #REF! |  | 39299.3333 |  |  | 533.664 | 800.5776 | 4483.6915 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | 3274.9444 | #REF! | 39299.3333 | 35292.4331 | -4006.9002
Other costs |  | BM-00110021_003 | BM-00110021_003_00000004 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Operation | Other cost | (blank) | other cost | [5 empty] | 20000 | 30000 | 20000 | 30000 | 20000 | 30000 |  | 203.7 |  | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | #REF! | 20000 | 16870.3667 | -3129.6333
E2E C-Hub System Team | Service Delivery OPS & Support | BM-00110021_002 |  | Customer Cloud Integration / pre-development for VI integration | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | Modoc, Daniel Stefan | 100% | Alex/Ann - tbc | 100% | #REF! | #REF! | #REF! | 78598.6667 | 0 | #REF! |  | 78598.6667 |  |  | 23035.968 | 8112.5197 | 9394.4013 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | 6549.8889 | #REF! | 78598.6667 | 99491.889 | 20893.2223
E2E C-Hub System Team | System Eng. & Feature Owners | BM-00110021_002 |  | E2E System Team - Requirements Eng. & System development | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | Personnel cost | Praveen, K M | 100% | Alexander | 100% | #REF! | #REF! | #REF! | 52462.84 | 0 | #REF! |  | 52462.84 |  |  | 4166.1956 | 4107.1233 | 4146.7853 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | 4371.9033 | #REF! | 52462.84 | 51767.2342 | -695.6058
E2E C-Hub System Team | System Eng. & Feature Owners | BM-00110021_002 |  | E2E System Team - SysArch - Requirements Eng. & System development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Personnel cost | Hategan, Liviu Ioan; Oliver J. | 200% | Alex/Alkis - tbc | 200% | #REF! | #REF! | #REF! | 157197.3333 | 0 | #REF! |  | 157197.3333 |  | tbd w/ Alin: who is staffed here | 20492.6976 | 25618.4832 | 23699.5123 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | 13099.7778 | #REF! | 157197.3333 | 187708.6931 | 30511.3598
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_003 |  | System integration and performing V&V | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | Personnel cost | Blohm, Christina; Frank, Kornelius | 100% | Alkis | 31.64% | #REF! | #REF! | #REF! | 71785.7143 | 0 | #REF! |  | 71785.7143 |  |  | 5752.3 | 6874.7 | 12346.4 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | 5982.1429 | #REF! | 71785.7143 | 78812.6857 | 7026.9714
E2E C-Hub System Team | Service Delivery OPS & Support | BM-00110021_003 |  | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | PA-CS | Personnel cost | Perless, Alexander | 100% | Target resp. | 100% | #REF! | #REF! | #REF! | 210721.5 |  | #REF! |  | 210721.5 |  |  | 19750.5 | 11768.625 | 21235.5 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | 17560.125 | #REF! | 210721.5 | 210795.75 | 74.25
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_002 |  | Managing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Personnel cost | Fagarasi, Lorand | 100% | Alkis - tbc | 100% | #REF! | #REF! | #REF! | 81437 | 0 | #REF! |  | 81437 |  |  | 6724.1664 | 3842.7725 | 9394.4013 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | #REF! | 81437 | 81039.0902 | -397.9098
E2E C-Hub System Team | Sys-Integration & Testing | BM-00110021_002 |  | Performing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Personnel cost | Chirlejan, Alex Bogdan | 100% | Alkis - tbc | 100% | #REF! | #REF! | #REF! | 81437 | 0 | #REF! |  | 81437 |  |  | 6403.968 | 8539.4944 | 9394.4013 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | 6786.4167 | #REF! | 81437 | 85415.6137 | 3978.6137
|  | BM-00110021_002 |  | Installation App development | PS-SC/PAC Other Costs | Operation | Other cost | [7 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0
XC-CP | Stretch target | BM-00110021_004 |  | Stretch target XC | PS-SC/PAC Other Costs | XC | Stretch target |  |  |  | 0 |  |  |  | -286993.92 | 0 | -286993.92 |  | -343003.9503 |  | CF05: Stretch target increased to compensate for the XC increase |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | -343003.9503 | 0 | 343003.9503
[24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | BM-00112873_001 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
Total | [14 empty] | 5492624.6504 | 1981950.9497 | #REF! | #REF! | 4885188.7183 | 2070962.4221 |  | 216492.3007 | 301641.0247 | 817488.5252 | 496490.5002 | 496490.5002 | 496490.5002 | 496490.5002 | 496490.5002 | 496490.5002 | 496490.5002 | 496490.5002 | 458028.5002 | #REF! | 4885188.7183 | #REF! | #REF!
5420000
[17 empty] | #REF! |  | 56009.9503
ECP Planning
|  |  |  | ECP / xyz1 | abc | [6 empty] | 1500 | 80
|  |  |  | ECP / xyz2 | abc | [6 empty] | 1496 | 150
|  |  |  | ECP / xyz3 | abc | [6 empty] | 1496 | 120
222
166
166
180
525
119
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hodzic Alkis (PS-CV/EES PS-SC/XPS) macht es Sinn die Aufgaben von Manish nach Cluj zu transferieren? Reply: JA wie besprochen.
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be transfered to Cluj M2026
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 002 to 003: all resource groups in Germany should be at 003. Need to be changed in MCR also.
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP)
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 003 to 002: all resource groups in Germany should be at 003. Need to be changed in MCR also.
Note on L23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Input Rainer from 20-Nov-25: Move plan for "Lakshmi" from 35% to 50%
Note on F24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP) Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from India to Cluj
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 003 to 002: all resource groups in Germany should be at 003. Need to be changed in MCR also.
Note on W51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes booking of Frank David = 16632 EUR in Jan-26.
Note on C54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 002 to 003: all resource groups in Germany should be at 003. Need to be changed in MCR also.

## Risk-Tracking
No | Risks | Risk amount(k€) | thereof included in Risk BP26 (BM-00107793_002) | Cost coverage ensured elsewhere | Remaining risk amount | Responsible | Customer | Column1 | Comment Stan | Consider? | Column2 | Hinweis LL | Risks PPT (Mar-26)
1 | Risk BP26 | 2080 |  |  | 2080 | C-Hub Customers | all | [5 empty] | Customer integrations | 250
2 | NA (currently not booking) | 840 | 420 |  | 420 | C-Hub Product | Penske, Amazon, ViaScience |  | 9-Mar-26: NA bookings added manually to the Cost tracking |  |  |  | MA for vehicle configuration | 68
3 | Budget cut CF02 | 400 |  |  | 400 | C-Hub Product | [6 empty] | NA Team + other cost | 423
4 | Refunding ögP | 330 |  |  | 330 | C-Hub Product |  |  |  |  | 96 | Planung aktuell Transfer <26 Werte in Diskussion | Operations L1/L2 Incident/Problem/Monitoring | 78
5 | Risk to overshoot ECP budget beyond ögP funding | 300 |  |  | 300 | ECP / PAC2 |  | see OneNote |  |  | 300 | Risiko verstsehe ich nicht ist Kostenneutral ECP Anteil wird von ÖGP bezhalt | Service Operation EU - VI | 100
6 | Service Improvements (Fleet Session 02.2026) | 230 |  |  | 230 | C-Hub Customers | Penske | see OneNote |  |  |  |  | Service Operation NA - VI | 100
7 | Manual Monitoring Penske | 50 | 50 |  | 0 | C-Hub Customers | Penske | see OneNote |  |  |  |  | Partner Manager | 41
8 | Unplanned additional effort ViaScience | 100 |  |  | 100 | C-Hub Customers | ViaScience | see OneNote |  |  |  |  | C-Hub XC New Features | 287
9 | Penske Volume increase (e.g. raw material) | 66 |  | 66 | 0 | PDCL | Penske | see OneNote |  | Not concidered |  |  | ETAS-MSS Cojali | 113
10 | SAE Licence | 40 |  | 40 | 0 | PDCL | Penske |  |  | Not concidered |  |  | R&D at Cojali | 300
11 | unplanned effort Heex | 20 |  |  | 20 | C-Hub Product / PS-SC/XPS | [6 empty] | VCS R&D | 293
12 | Proprietary CAN Messages Volvo for Remodul | 10 |  |  | 10 | C-Hub Product | Remodul |  |  |  | 10 | müsste doch in Remodul rein | Other cost / Lab, HW etc. | 30
13 | Additional effort WoW | 100 |  |  | 100 | C-Hub Product |  | see OneNote | [5 empty] | 2083
14 | LTB eMMC | 160 |  |  | 160 | PDCL
15 | Penske additional effort secure cloud connection | 50 |  |  | 50 | C-Hub Product | Penske | see OneNote
16 | Logistic support C/TMS | 56 |  | 56 | 0 | PDCL |  | see OneNote |  | Not concidered |  |  | Refunding ögP | 330
17 | Operative logistics | 35 |  | 35 | 0 | PDCL |  | see OneNote |  |  | 35 | muss auf die Logistik Kostenstell | Budget cut CF02 | 400
18 | additiona MAE invest for higher Penske volume | 10 |  |  | 10 | PDCL |  |  |  | Not concidered |  |  | ECP | 300
19 | CARB CTC Certification | 170 |  |  | 170 | C-Hub Product | Penske | [5 empty] | Service Improvements (Fleet Session xx.02.2026) | 230
20 | Antenna Homologation | 60 |  |  | 60 | C-Hub Customers | Penske | [5 empty] | Manual Monitoring Penske | 50
21 | Mexico Certification | 50 |  |  | 50 | C-Hub Customers | new customers | [5 empty] | Unplanned additional effort ViaScience | 250
Total |  | 4490 | 470 | 0 | 4020 | [5 empty] | 106 |  | unplanned effort Heex | 20
|  | 58462.4221 | [10 empty] | Propietary CAN Messages Volvo for Remodul | 10
[13 empty] | Additional effort WoW | 100
|  | 5157 | 940 |  |  | 4217 | 4055 |  | 170 |  |  |  | LTB eMMC | 160
[13 empty] | Penske additional effort secure cloud connection | 50
[13 empty] | Operative logistics | 35
PPC
|  | 4070 |  |  |  | eigene Spalte --> Maßnahme/Finanzierung sichergestellt | [6 empty] | CARB CTC Certification | 170
[13 empty] | Antenna Homologation | 60
[13 empty] | Mexico Certification | 50
2215
| Bottom-up | 9
| first measure to reduce budget demand |  | -1.5
| BP26 pre-steering incl. measures | 7.5
| Top down budget cut for BP26 and introduction of risks maintaned in Cust-Proj-Ext MCR plan (xxx) |  | -2.08
| BP26 top-down | 5.5
| Top down budget cut for CF02/CF05 |  | -0.4
| CF02 | 5.1
5.5
| BizCase PRM | 6.05
Mapping of the YTD gap (as of 4-Apr-26) to the financial risks
| Task Name | CF05 C-Hub PF | Estimated at completion (based on YTD actuals, 4-Apr'26) | Gap (Prognosis vs. Plan) | Mapping to existing risk? | Initial planned risk amount | Delta planned risk amount vs. YTD gap | Risk reasoning | Risk status | Realized risk amount | Actual needed risk amount
| Stretch target (budget cut) | -400000 | 0 | 400000 | Budget cut CF02 | 400000 | 0 | No real cost saving measures for 400 K€ defined. | Identified |  | 400000
| Stretch target XC | -343003.9503 | 0 | 343003.9503 | BP26 (BM-00107793_002) -> C-Hub XC New Features | 343003.9503 | 0 | No real cost saving measures for 343 K€ defined. | Realized | 56009.9503 | 343003.9503
| PO for Cojali | 180000 | 332000 | 152000 | BP26 (BM-00107793_002)->VCS R&D |  | 152000 | VCS total cost 1378 K€ | Identified |  | 152000
| VCS R&D | 682500 | 824000 | 141500 | BP26 (BM-00107793_002)->VCS R&D | 292500 | -151000 | VCS total cost 1378 K€ | Identified |  | 141500
| ETAS-MSS Cojali | 150000 | 277605 | 127605 | BP26 (BM-00107793_002)->ETAS-MSS Cojali | 113000 | 14605 |  | Realized | 127605 | 127605
| E2E System Team - SysArch - Requirements Eng. & System development | 157197.3333 | 187708.6931 | 30511.3598 | Gap is not mapped to risk |  | 30511.3598 |  | Identified |  | 30511.3598
| Customer Cloud Integration / pre-development for VI integration | 78598.6667 | 99491.889 | 20893.2223 | Gap is not mapped to risk |  | 20893.2223 |  | Identified |  | 20893.2223
| Security Manager | 19649.6667 | 29468.3348 | 9818.6681 | Gap is not mapped to risk |  | 9818.6681 |  | Identified |  | 9818.6681
| Performing V&V | 81437 | 85415.6137 | 3978.6137 | Gap is not mapped to risk |  | 3978.6137 |  | Identified |  | 3978.6137
| Product development lead | 226865.1 | 229309.126 | 2444.026 | Gap is not mapped to risk |  | 2444.026 |  | Identified |  | 2444.026
| Service Management | 81435.7843 | 83713.8067 | 2278.0224 | Gap is not mapped to risk |  | 2278.0224 |  | Identified |  | 2278.0224
| Partner Manager | 40717.8922 | 42387.109 | 1669.2169 | BP26 (BM-00107793_002)->Partner Manager | 40717.8922 | -39048.6753 |  | Identified |  | 1669.2169
| System Integration and Solution Architecture technical customer support | 210721.5 | 210795.75 | 74.25 | Gap is not mapped to risk |  | 74.25 |  | Identified |  | 74.25
| NA Team + other cost | 423141.913 | 846283.8551 | 423141.942 | BP26 (BM-00107793_002)->NA Team + other cost | 423141.913 | 0.028986 |  | Identified |  | 423141.942
| Series Logistics Concept | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| Data / rev. Eng. and AI | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| C-Hub XC - HW Change for RS-232, K-LINE | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| C-Hub XC New Features | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| Refunding for C-Hub XC ögP | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| BD Support (Cojali & CDK) | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| BD Support (Technical Documentation) | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| Customer integrations | 0 | 0 | 0 | BP26 (BM-00107793_002)->Customer integrations | 250000 | -250000 |  | Identified |  | 0
| Installation App development | 0 | 0 | 0 | Currently no gap |  | 0 |  |  |  | 0
| CVIT Partner Manager | 98689.3394 | 98689.3394 | 0 | Currently no gap |  | 0 |  |  |  | 0
| Refunding for C-Hub main project ögP | -330000 | 0 | 330000 | Refunding ögP | 330000 | 0 |  | Identified |  | 330000
| BD Support (PjM and Controlling) | 578153.672 | 578153.254 | -0.418 | Currently no gap |  | -0.418 |  |  |  | -0.418
| Support BGSW (Arun) | 19721.52 | 19485.2903 | -236.2297 | Gap is not mapped to risk |  | -236.2297 |  | Identified |  | -236.2297
| Managing V&V | 81437 | 81039.0902 | -397.9098 | Gap is not mapped to risk |  | -397.9098 |  | Identified |  | -397.9098
| E2E System Team - Requirements Eng. & System development | 52462.84 | 51767.2342 | -695.6058 | Gap is not mapped to risk |  | -695.6058 |  | Identified |  | -695.6058
| EPQ | 26231.42 | 24979.6249 | -1251.7951 | Gap is not mapped to risk |  | -1251.7951 |  | Identified |  | -1251.7951
| Operations L1/L2 Incident/Problem/Monitoring | 117898 | 115803.3355 | -2094.6645 | BP26 (BM-00107793_002)->Operations L1/L2 Incident/Problem/Monitoring | 78598.6667 | -80693.3311 |  | Identified |  | -2094.6645
| Other cost / Lab, HW etc. | 20000 | 16870.3667 | -3129.6333 | BP26 (BM-00107793_002)->Other cost / Lab, HW etc. | 30000 | -33129.6333 |  | Identified |  | -3129.6333
| Technical Docu Cluj | 39299.3333 | 35292.4331 | -4006.9002 | Gap is not mapped to risk |  | -4006.9002 |  | Identified |  | -4006.9002
| Service Operation EU - VI | 25000 | 18750 | -6250 | BP26 (BM-00107793_002)->Service Operation EU - VI | 100000 | -106250 |  | Identified |  | -6250
| Service Operation NA - VI | 25000 | 18750 | -6250 | BP26 (BM-00107793_002)->Service Operation NA - VI | 100000 | -106250 |  | Identified |  | -6250
| R&D at Cojali | 60000 | 50000 | -10000 | BP26 (BM-00107793_002)->R&D at Cojali | 300000 | -310000 |  | Identified |  | -10000
| CDK development | 78598.6667 | 66848.1411 | -11750.5255 | Gap is not mapped to risk |  | -11750.5255 |  | Identified |  | -11750.5255
| RM+RD config + Cojali + Pantaris configs | 131061.5067 | 110716.2342 | -20345.2725 | Gap is not mapped to risk |  | -20345.2725 |  | Identified |  | -20345.2725
| System integration and performing V&V | 196374.5143 | 172254.2857 | -24120.2286 | Gap is not mapped to risk |  | -24120.2286 |  | Identified |  | -24120.2286
| MA for vehicle configuration | 210000 | 184135.01 | -25864.99 | BP26 (BM-00107793_002)->MA for vehicle configuration | 67500 | -93364.99 |  | Identified |  | -25864.99
| C-Hub XC Series Care_005 | 611000 | 569604.2708 | -41395.7292 | Gap is not mapped to risk |  | -41395.7292 |  | Identified |  | -41395.7292
| C-Hub XC Series Care_004 | 1095000 | 975412.0298 | -119587.9702 | Gap is not mapped to risk |  | -119587.9702 |  | Identified |  | -119587.9702
| VCS SW maintance | 370000 | 222000 | -148000 | BP26 (BM-00107793_002)->VCS R&D |  | -148000 | VCS total cost 1378 K€ | Identified |  | -148000
| Financial risk - not planned in MCR |  | 230000 | 230000 | Service Improvements (Fleet Session 02.2026) | 230000 | 0 |  | Identified |  | 230000
| Financial risk - not planned in MCR |  | 100000 | 100000 | Unplanned additional effort ViaScience | 100000 | 0 |  | Identified |  | 100000
| Financial risk - not planned in MCR |  | 10000 | 10000 | Propietary CAN Messages Volvo for Remodul | 10000 | 0 |  | Realized | 25000 | 10000
| Financial risk - not planned in MCR |  | 100000 | 100000 | Additional effort WoW | 100000 | 0 |  | Realized | 50000 | 100000
| Financial risk - not planned in MCR |  | 50000 | 50000 | Penske additional effort secure cloud connection | 50000 | 0 |  | Identified |  | 50000
| Financial risk - not planned in MCR |  | 170000 | 170000 | CARB CTC Certification | 170000 | 0 |  | Identified |  | 170000
| Financial risk - not planned in MCR |  | 60000 | 60000 | Antenna Homologation | 60000 | 0 |  | Identified |  | 60000
| Financial risk - not planned in MCR |  | 50000 | 50000 | Mexico Certification | 50000 | 0 |  | Identified |  | 50000
| Financial risk - not planned in MCR |  | 420000 | 420000 | NA (currently not booking) | 420000 | 0 |  | Identified |  | 420000
| Grand Total | 5095188.7183 | 7848729.1172 | 2753540.3989 |  | 4058462.4221 | -1304922.0232 |  |  | 258614.9503 | 2753540.3989
7848729.1172
7848729.1172
| Mapping Financial risk <-> Task | Sum of Gap (Prognosis vs. Plan) | Sum of Exisitng risk amount | Sum of Uncovered risk amount
| BP26 (BM-00107793_002)->ETAS-MSS Cojali | 127605 | 113000 | 14605
| ETAS-MSS Cojali | 127605 | 113000 | 14605
| BP26 (BM-00107793_002)->NA Team + other cost | 423141.942 | 423141.913 | 0.028986
| NA Team + other cost | 423141.942 | 423141.913 | 0.028986
| Mexico Certification |  | 50000 | 0
| (blank) |  | 50000 | 0
| Budget cut CF02 | 400000 | 400000 | 0
| Stretch target (budget cut) | 400000 | 400000 | 0
| Refunding ögP | 330000 | 330000 | 0
| Refunding for C-Hub main project ögP | 330000 | 330000 | 0
| Antenna Homologation |  | 60000 | 0
| (blank) |  | 60000 | 0
| CARB CTC Certification |  | 170000 | 0
| (blank) |  | 170000 | 0
| NA (currently not booking) |  | 420000 | 0
| (blank) |  | 420000 | 0
| BP26 (BM-00107793_002) -> C-Hub XC New Features | 343003.9503 | 343003.9503 | 0
| Stretch target XC | 343003.9503 | 343003.9503 | 0
| Penske additional effort secure cloud connection |  | 50000 | 0
| (blank) |  | 50000 | 0
| Propietary CAN Messages Volvo for Remodul |  | 10000 | 0
| (blank) |  | 10000 | 0
| Unplanned additional effort ViaScience |  | 100000 | 0
| (blank) |  | 100000 | 0
| Service Improvements (Fleet Session 02.2026) |  | 230000 | 0
| (blank) |  | 230000 | 0
| Additional effort WoW |  | 100000 | 0
| (blank) |  | 100000 | 0
| (blank) | -0.418 |  | -0.418
| BD Support (Cojali & CDK) | 0 |  | 0
| BD Support (PjM and Controlling) | -0.418 |  | -0.418
| BD Support (Technical Documentation) | 0 |  | 0
| C-Hub XC - HW Change for RS-232, K-LINE | 0 |  | 0
| C-Hub XC New Features | 0 |  | 0
| CVIT Partner Manager | 0 |  | 0
| Data / rev. Eng. and AI | 0 |  | 0
| Installation App development | 0 |  | 0
| Refunding for C-Hub XC ögP | 0 |  | 0
| Series Logistics Concept | 0 |  | 0
| BP26 (BM-00107793_002)->Other cost / Lab, HW etc. | -3129.6333 | 30000 | -33129.6333
| Other cost / Lab, HW etc. | -3129.6333 | 30000 | -33129.6333
| BP26 (BM-00107793_002)->Partner Manager | 1669.2169 | 40717.8922 | -39048.6753
| Partner Manager | 1669.2169 | 40717.8922 | -39048.6753
| BP26 (BM-00107793_002)->Operations L1/L2 Incident/Problem/Monitoring | -2094.6645 | 78598.6667 | -80693.3311
| Operations L1/L2 Incident/Problem/Monitoring | -2094.6645 | 78598.6667 | -80693.3311
| BP26 (BM-00107793_002)->MA for vehicle configuration | -25864.99 | 67500 | -93364.99
| MA for vehicle configuration | -25864.99 | 67500 | -93364.99
| BP26 (BM-00107793_002)->Service Operation EU - VI | -6250 | 100000 | -106250
| Service Operation EU - VI | -6250 | 100000 | -106250
| BP26 (BM-00107793_002)->Service Operation NA - VI | -6250 | 100000 | -106250
| Service Operation NA - VI | -6250 | 100000 | -106250
| BP26 (BM-00107793_002)->VCS R&D | 145500 | 292500 | -147000
| PO for Cojali | 152000 |  | 152000
| VCS R&D | 141500 | 292500 | -151000
| VCS SW maintance | -148000 |  | -148000
| Gap is not mapped to risk | -153790.0044 |  | -153790.0044
| CDK development | -11750.5255 |  | -11750.5255
| C-Hub XC Series Care_004 | -119587.9702 |  | -119587.9702
| C-Hub XC Series Care_005 | -41395.7292 |  | -41395.7292
| Customer Cloud Integration / pre-development for VI integration | 20893.2223 |  | 20893.2223
| E2E System Team - Requirements Eng. & System development | -695.6058 |  | -695.6058
| E2E System Team - SysArch - Requirements Eng. & System development | 30511.3598 |  | 30511.3598
| EPQ | -1251.7951 |  | -1251.7951
| Managing V&V | -397.9098 |  | -397.9098
| Performing V&V | 3978.6137 |  | 3978.6137
| Product development lead | 2444.026 |  | 2444.026
| RM+RD config + Cojali + Pantaris configs | -20345.2725 |  | -20345.2725
| Security Manager | 9818.6681 |  | 9818.6681
| Service Management | 2278.0224 |  | 2278.0224
| Support BGSW (Arun) | -236.2297 |  | -236.2297
| System integration and performing V&V | -24120.2286 |  | -24120.2286
| System Integration and Solution Architecture technical customer support | 74.25 |  | 74.25
| Technical Docu Cluj | -4006.9002 |  | -4006.9002
| BP26 (BM-00107793_002)->Customer integrations | 0 | 250000 | -250000
| Customer integrations | 0 | 250000 | -250000
| BP26 (BM-00107793_002)->R&D at Cojali | -10000 | 300000 | -310000
| R&D at Cojali | -10000 | 300000 | -310000
| Grand Total | 1563540.3989 | 4058462.4221 | -1304922.0232
| Risks | Sum of Gap (Prognosis vs. Plan) | Sum of Exisitng risk amount | Sum of Uncovered risk amount | Sum of Realized risk amount
| Identified | 1092931.8667 | 3492458.4719 | -1319526.6052
| Antenna Homologation |  | 60000 | 0
| BP26 (BM-00107793_002)->Customer integrations | 0 | 250000 | -250000
| BP26 (BM-00107793_002)->MA for vehicle configuration | -25864.99 | 67500 | -93364.99
| BP26 (BM-00107793_002)->NA Team + other cost | 423141.942 | 423141.913 | 0.028986
| BP26 (BM-00107793_002)->Operations L1/L2 Incident/Problem/Monitoring | -2094.6645 | 78598.6667 | -80693.3311
| BP26 (BM-00107793_002)->Other cost / Lab, HW etc. | -3129.6333 | 30000 | -33129.6333
| BP26 (BM-00107793_002)->Partner Manager | 1669.2169 | 40717.8922 | -39048.6753
| BP26 (BM-00107793_002)->R&D at Cojali | -10000 | 300000 | -310000
| BP26 (BM-00107793_002)->Service Operation EU - VI | -6250 | 100000 | -106250
| BP26 (BM-00107793_002)->Service Operation NA - VI | -6250 | 100000 | -106250
| BP26 (BM-00107793_002)->VCS R&D | 145500 | 292500 | -147000
| Budget cut CF02 | 400000 | 400000 | 0
| CARB CTC Certification |  | 170000 | 0
| Gap is not mapped to risk | -153790.0044 |  | -153790.0044
| Mexico Certification |  | 50000 | 0
| NA (currently not booking) |  | 420000 | 0
| Penske additional effort secure cloud connection |  | 50000 | 0
| Refunding ögP | 330000 | 330000 | 0
| Service Improvements (Fleet Session 02.2026) |  | 230000 | 0
| Unplanned additional effort ViaScience |  | 100000 | 0
| Realized | 470608.9503 | 566003.9503 | 14605 | 258614.9503
| Additional effort WoW |  | 100000 | 0 | 50000
| BP26 (BM-00107793_002) -> C-Hub XC New Features | 343003.9503 | 343003.9503 | 0 | 56009.9503
| BP26 (BM-00107793_002)->ETAS-MSS Cojali | 127605 | 113000 | 14605 | 127605
| Propietary CAN Messages Volvo for Remodul |  | 10000 | 0 | 25000
| Grand Total | 1563540.8169 | 4058462.4221 | -1304921.6052 | 258614.9503
Risks status legend:
Identified: The risk has been identified, but not yet threated.
Mitigated: A mitigation plan is in place and the risk is being actively managed.
Accepted: The organization has accepted the potential impact without taking active mitigation.
Realized: The risk has occurred and become an active issue.
Closed: The risk is no longer considered a threat, usually because its probability is zero.
Postponed: Monitoring the risk is delayed until a later time.

## Cost tracking chart
| Actuals | Actuals | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Prognosis | Act Mar-25 | Act Apr-25 | Act May-25 | Act Jun-25 | Act Jul-25 | Act Aug-25 | Act Sep-25 | Act Oct-25 | Act Nov-25 | Act Dec-25
Cumulative actuals | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 |  |  |  | 213333.3333 | 23703.7037
C-Hub Actuals (BM-00110021_001) | 216492.3007 | 540087.1754 | 1379756.8607 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23703.7037
Actuals not yet transferred to MCR | 65439.7949 | 108925.7399 | 180226.6776 | [9 empty] | 50000
C-Hub All Actuals (incl. not yet transferred) | 281932.0957 | 649012.9153 | 1559983.5383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 23333.3333 | 0 | 0 | 0
Plan CF02 (BM-00110021_001) | 407099.0599 | 814198.1197 | 1221297.1796 | 1628396.2394 | 2035495.2993 | 2442594.3591 | 2849693.419 | 3256792.4788 | 3663891.5387 | 4070990.5986 | 4478089.6584 | 4885188.7183 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037 | 23703.7037
Prognosis 2026 (based on YTD actuals) |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 49629.6296 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -23703.7037 | -23703.7037 | 0
Gap (Actuals vs Plan), in € | -125166.9642 | -165185.2044 | 338686.3587 | -1628396.2394 | -2035495.2993 | -2442594.3591 | -2849693.419 | -3256792.4788 | -3663891.5387 | -4070990.5986 | -4478089.6584 | -4885188.7183 | 49629.6296 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -370.3704 | -23703.7037 | -23703.7037 | 0
Gap (Prognosis vs Plan), in % | -30.75% | -20.29% | 27.73%
Customer ext. project (BM-00107793_002) | [11 empty] | 2070962.4221
Financial risks | [11 empty] | 700000
7656151.1404
7848729.1172
3894077.492
|  | 6200938.9662 | [9 empty] | -192577.9768

## Dashboards
New MCR ID | (All)
Task Name (all sub-projects) | Sum of CF05 C-Hub PF | Estimated at completion (Gap as number) | Gap (Prognosis vs. Plan)
Stretch target (budget cut) | -400000 | 0 | 400000
Stretch target XC | -343003.9503 | 0 | 343003.9503
PO for Cojali | 180000 | 332000 | 152000
VCS R&D | 682500 | 824000 | 141500
ETAS-MSS Cojali | 150000 | 277605 | 127605
E2E System Team - SysArch - Requirements Eng. & System development | 157197.3333 | 187708.6931 | 30511.3598
Customer Cloud Integration / pre-development for VI integration | 78598.6667 | 99491.889 | 20893.2223
Security Manager | 19649.6667 | 29468.3348 | 9818.6681
Performing V&V | 81437 | 85415.6137 | 3978.6137
Product development lead | 226865.1 | 229309.126 | 2444.026
Service Management | 81435.7843 | 83713.8067 | 2278.0224
Partner Manager | 40717.8922 | 42387.109 | 1669.2169
System Integration and Solution Architecture technical customer support | 210721.5 | 210795.75 | 74.25
NA Team + other cost | 423141.913 | 423141.9275 | 0.014493
Series Logistics Concept | 0 | 0 | 0
Data / rev. Eng. and AI | 0 | 0 | 0
C-Hub XC - HW Change for RS-232, K-LINE | 0 | 0 | 0
C-Hub XC New Features | 0 | 0 | 0
Refunding for C-Hub XC ögP | 0 | 0 | 0
BD Support (Cojali & CDK) | 0 | 0 | 0
BD Support (Technical Documentation) | 0 | 0 | 0
Customer integrations | 0 | 0 | 0
Installation App development | 0 | 0 | 0
CVIT Partner Manager | 98689.3394 | 98689.3394 | 0
Refunding for C-Hub main project ögP | -330000 | -330000 | 0
BD Support (PjM and Controlling) | 578153.672 | 578153.254 | -0.418
Support BGSW (Arun) | 19721.52 | 19485.2903 | -236.2297
Managing V&V | 81437 | 81039.0902 | -397.9098
E2E System Team - Requirements Eng. & System development | 52462.84 | 51767.2342 | -695.6058
EPQ | 26231.42 | 24979.6249 | -1251.7951
Operations L1/L2 Incident/Problem/Monitoring | 117898 | 115803.3355 | -2094.6645
Other cost / Lab, HW etc. | 20000 | 16870.3667 | -3129.6333
Technical Docu Cluj | 39299.3333 | 35292.4331 | -4006.9002
Service Operation EU - VI | 25000 | 18750 | -6250
Service Operation NA - VI | 25000 | 18750 | -6250
R&D at Cojali | 60000 | 50000 | -10000
CDK development | 78598.6667 | 66848.1411 | -11750.5255
RM+RD config + Cojali + Pantaris configs | 131061.5067 | 110716.2342 | -20345.2725
System integration and performing V&V | 196374.5143 | 172254.2857 | -24120.2286
MA for vehicle configuration | 210000 | 184135.01 | -25864.99
C-Hub XC Series Care_005 | 611000 | 569604.2708 | -41395.7292
C-Hub XC Series Care_004 | 1095000 | 975412.0298 | -119587.9702
VCS SW maintance | 370000 | 222000 | -148000
Grand Total | 5095188.7183 | 5905587.1897 | 810398.4714
XC only | Sum of CF05 C-Hub PF | Prognosis (based on YTD actuals) | Gap (Porgnosis vs. Plan)
XC | 1362996.0497 | 1545016.3006 | 182020.2508
C-Hub XC - HW Change for RS-232, K-LINE | 0 | 0 | 0
C-Hub XC New Features | 0 | 0 | 0
C-Hub XC Series Care_004 | 1095000 | 975412.0298 | -119587.9702
C-Hub XC Series Care_005 | 611000 | 569604.2708 | -41395.7292
Stretch target XC | -343003.9503 | 0 | 343003.9503
Grand Total | 1362996.0497 | 1545016.3006 | 182020.2508
VCS only | Sum of CF05 C-Hub PF | Prognosis (based on YTD actuals) | Gap (Porgnosis vs. Plan)
VCS | 1232500 | 1378000 | 145500
PO for Cojali | 180000 | 332000 | 152000
VCS R&D | 682500 | 824000 | 141500
VCS SW maintance | 370000 | 222000 | -148000
Grand Total | 1232500 | 1378000 | 145500
Cost tracking by "New Team bucket" | Sum of CF05 C-Hub PF | Sum of EAC (based on YTD actuals) | Gap (Porgnosis vs. Plan)
Container App Development | 78598.6667 | 66848.1411 | -11750.5255
HW & BSW | 1706000 | 1545016.3006 | -160983.6994
NA ENG Team | 423141.913 | 423141.9275 | 0.014493
Partner Management | 40717.8922 | 42387.109 | 1669.2169
Premium Multi-Brand Data | 180000 | 332000 | 152000
Refunding | -330000 | -330000 | 0
Service Delivery OPS & Support | 541116.791 | 561572.0154 | 20455.2244
Stretch target | -743003.9503 | 0 | 743003.9503
Supporting Functions | 65602.6067 | 73933.2499 | 8330.6433
Sys-Integration & Testing | 625412.9476 | 603310.5487 | -22102.3989
System Eng. & Feature Owners | 209660.1733 | 239475.9273 | 29815.754
(blank) | 2297941.678 | 2347901.97 | 49960.292
Grand Total | 5095188.7183 | 5905587.1897 | 810398.4714
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Final input Arun 002&003 (hidden)
New MCR ID | Task name | Resource group | Orga | Orga new | Cost type | Person booking | Hrs | Amount
BM-00110021_003 | Refunding for C-Hub main project ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding |  |  | Refunding | (blank) |  | -330000
BM-00110021_002 | Customer integrations | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | assumtption: 10 customer á 80k€ |  | 0
BM-00110021_002 | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | Dirk needed for tranfer to PS |  | 202500
BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 1496 | 78598.6667
BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Dhingra, Manish | 1871 | 52469
BM-00110021_002 | Data / rev. Eng. and AI | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | (blank) |  | 0
BM-00110021_002 | Series Logistics Concept | PS-SC/PAC Other Costs | M | M | Other cost | (blank) |  | 0
BM-00110021_002 | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | PA-CS/NA | Personnel cost |  | 3720 | 423141.913
BM-00110021_002 | VCS SW maintance | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 370000
BM-00110021_002 | System integration and performing V&V | PS-SC/XPS PS-SC XPS development | PA-CS | PA-CS | Personnel cost | Patrick, has not booked yet. | 721 | 124588.8
BM-00110021_002 | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Sorina + tbd | 2244 | 117898
BM-00110021_002 | Service Management | PS-SC/ETX | Cluj | Cluj | Personnel cost | Lausch, Ann Kathrin / Cluj PS-SC/ETX | 1550 | 81435.7843
BM-00110021_002 | Service Operation EU - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 50000
BM-00110021_002 | Service Operation NA - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 50000
BM-00110021_003 | Partner Manager | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Hornung, Floyd? | 283.8 | 42144.3
BM-00110021_002 | EPQ | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Lakshmi, Ramakrishnan | 654.85 | 18361.994
BM-00110021_002 | Security Manager | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | IN | Personnel cost | Shashikumar, Nagaraju; Khandelwal, Priti | 374 | 19649.6667
BM-00110021_002 | Support BGSW (Arun) | MS/END-IN_iGPM Mechanical_Design_Services_W/O_CAD_SW_PS_Sensors | IN | IN | Personnel cost | Palanisamy, Babu | 936 | 19721.52
BM-00110021_002 | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | BD | BD | Other cost | Marianne, Nina |  | 87000
BM-00110021_003 | Product development lead | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | CV | Personnel cost | Hodzic, Alkis -> Transfer Alkis to PS-S -> C reduces costs | 1617 | 226865.1
BM-00110021_002 | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | BD | BD | Other cost | Rainer, Stan |  | 355125
BM-00110021_002 | CVIT Partner Manager | PS-SC/PAC Other Costs | Bari | Bari | Other cost | (blank) |  | 98689.3394
BM-00110021_002 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | (blank) |  | 80000
BM-00110021_002 | R&D at Cojali | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 90000
BM-00110021_002 | PO for Cojali | PS-SC/PAC Other Costs | VCS | VCS | Other cost | Scholz, Sebastian |  | 180000
BM-00110021_002 | VCS R&D | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 682500
BM-00110021_002 | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | BD | BD | Other cost | Gibayev Oleg |  | 136028.672
BM-00110021_003 | CDK development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 1496 | 78598.6667
BM-00110021_002 | Technical Docu Cluj | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 748 | 39299.3333
BM-00110021_003 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 20000
BM-00110021_002 | Customer Cloud Integration / pre-development for VI integration | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Modoc, Daniel Stefan | 1496 | 78598.6667
BM-00110021_002 | E2E System Team - Requirements Eng. & System development | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Praveen, K M | 1871 | 52462.84
BM-00110021_002 | E2E System Team - SysArch - Requirements Eng. & System development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Guias, Cornel Liviu; Hategan, Liviu Ioan; | 2992 | 157197.3333
BM-00110021_002 | System integration and performing V&V | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | CV | Personnel cost | Blohm, Christina; Frank, Kornelius | 511.6587 | 71785.7143
BM-00110021_003 | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Perless, Alexander | 1419 | 210721.5
BM-00110021_002 | Managing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Cluj | Personnel cost | Fagarasi, Lorand | 1550 | 81437
BM-00110021_002 | Performing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Cluj | Personnel cost | Chirlejan, Alex Bogdan | 1550 | 81437
BM-00110021_002 | Installation App development | PS-SC/PAC Other Costs | Operation | Operation | Other cost |  |  | 0
C-Hub Cust Ext - BM-00107793_002 | Customer integrations | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | assumtption: 10 customer á 80k€ |  | 250000
C-Hub Cust Ext - BM-00107793_002 | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | Dirk needed for tranfer to PS |  | 67500
C-Hub Cust Ext - BM-00107793_002 | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | PA-CS/NA | Personnel cost |  | 3720 | 423141.913
C-Hub Cust Ext - BM-00107793_002 | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Sorina + Bianca + Maria (200%) | 2244 | 78598.6667
C-Hub Cust Ext - BM-00107793_002 | Service Operation EU - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 75000
C-Hub Cust Ext - BM-00107793_002 | Service Operation NA - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 75000
C-Hub Cust Ext - BM-00107793_002 | Partner Manager | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Hornung, Floyd? | 425.7 | 63216.45
C-Hub Cust Ext - BM-00107793_002 | C-Hub XC New Features | PS-SC/PAC Other Costs | XC | XC | Other cost | Multiple |  | 286993.92
C-Hub Cust Ext - BM-00107793_002 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | (blank) |  | 70000
C-Hub Cust Ext - BM-00107793_002 | R&D at Cojali | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 270000
C-Hub Cust Ext - BM-00107793_002 | VCS R&D | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 292500
C-Hub Cust Ext - BM-00107793_002 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 30000
0
Input about BM-00107799_002 C-Hub Cust Ext :
- This should be new L1 number
- PDCL P00540 (PAC) / copy/paste from BM-00107799_001 number
- Status should be "PLAN"
- Once planned send YAP to Erhard for approval
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hodzic Alkis (PS-CV/EES PS-SC/XPS) macht es Sinn die Aufgaben von Manish nach Cluj zu transferieren? Reply: JA wie besprochen.
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be transfered to Cluj M2026
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP)
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP) Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from India to Cluj

## XC-fix (hidden)
green
1364375
626875
626875
55312.5
55312.5
BM-number | Task | C-Hub PF | C-Hub Cust Ext
004 | various (see Can's planning) | 940241.92
xxx | XC-CP Customer Extention (other cost) |  | 286993.92
004 | Stretch target (other cost) | -286993.92
005 | various (see Can's planning) | 711127
1364375
|  | 1588006.08 | 63362.84
63362.84
| 0.3234 | 626875 | -92815.086 | 534059.914
| 0.3234 | 626875 | -92815.086 | 534059.914
| 0.057071 | 110625 | -16379.1328 | 94245.8672
| 0.057071 | 110625 | -16379.1328 | 94245.8672
| 0.11952 | 231681.42 | -34302.7412 | 197378.6788
0
| 0.11952 | 231681.42 | -34302.7412 | 197378.6788
|  | 1938362.84 |  | 1651368.92
-286993.92

## AAA (hidden)
Team bucket | New MCR logic | New MCR ID | Task name | Resource group | Cost type | Person booking | new Team | delta to 2025 | consequence if canceled | FTE (%) 2026 | Hrs 2026 | Rate 2026 | Personnel costs | Column1 | MCR (Plan input) | Prognosis BP26 | C-Hub CF09/2025 (before redistribution to Cust. Proj) | Comments to Prognosis BP26 | Gap Pers. Vs. BP26
Refunding | Rest ögP, equivalent to _007 | BM-00110021_003 | Refunding for C-Hub main project ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding | Refunding | (blank) | - |  |  |  | #REF! | #REF! | #REF! | #REF! | 0 |  | #REF! |  | #REF!
Refunding | XC ögP, equivalent to_005 | BM-00110021_005 | Refunding for C-Hub XC ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding | Refunding | (blank) | - |  |  |  | #REF! | #REF! | #REF! | #REF! | 0 |  | #REF! |  | #REF!
Customer specific effort | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Customer integrations | PS-SC/PAC Other Costs | Other cost | assumtption: 10 customer á 80k€ | Customer specific | new |  |  | #REF! | #REF! | #REF! | #REF! | 800000 | 800000 |  |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | MA for vehicle configuration | PS-SC/PAC Other Costs | Other cost | Dirk needed for tranfer to PS | DaaS Delivery | constant | special know how for RD. No other person available. Lead: no standard diagnostics data or RD use cases like for TOP107, Austria, ECP | 100% | #REF! | #REF! | #REF! | #REF! | 270000 | 270000 | #REF! |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Transfer to PS (Vienna?) | DaaS Delivery | new | no transfer to PS possible | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 150000 |  |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Dhingra, Manish | DaaS Delivery | constant | no RM configs (CAN Data) for any use-case / required for DaaS | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 54000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Data / rev. Eng. and AI | PS-SC/PAC Other Costs | Other cost | (blank) | DaaS Delivery | new | LCV data not available; no support of EVs; support busses difficult | other cost | #REF! | #REF! |  | #VALUE! | 150000 | 150000 | #REF! |  | 150000
Other costs | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Series Logistics Concept | PS-SC/PAC Other Costs | Other cost | (blank) | Logistics | constant | no delivery to new customers possible; no handling of shortage etc. | other cost | #REF! | #REF! |  | #VALUE! | 67000 | 67000 | #REF! |  | 67000
NA Activities | Rest non-ögP, equivalent to _006 | BM-00110021_002 | NA Team + other cost | PS-EC EBR-NA SW Eng | Personnel cost |  | NA Localization | increasing | no NA customer acquisition support and no NA C-Hub. | pauschal top-down geschätzt | #REF! | #REF! | #VALUE! | #VALUE! | 790000 | 790000 |  |  | #VALUE!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | VCS SW maintance | PS-SC/PAC Other Costs | Other cost | (blank) | Operation of Service | constant | stop C-Hub | Walter/Rainer klärt mit Daniel | #REF! | #REF! | #VALUE! | #VALUE! | 400000 | 400000 | #REF! |  | #VALUE!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | System integration and performing V&V | PS-SC/XPS PS-SC XPS development | Personnel cost | Patrick, has not booked yet. | Operation of Service | constant | no customer support ww; E2E integration, testing, and release; no Remodul tech support | 100% | #REF! | 172.8 | #REF! | #REF! | #REF! | 160000 |  |  | #REF!
PjM, Biz Dev, service mng | Rest ögP, equivalent to _007 | BM-00110021_003 | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/PAC PAC1 | Personnel cost | Beck, Jochen --> transfer to Cluj | Operation of Service | constant | required for serivce delivery, OPS and support | 100% | #REF! | 148.5 | #REF! | #REF! | #REF! | 178000 | #REF! |  | #REF!
PjM, Biz Dev, service mng | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Service Management | PS-SC/ETX | Personnel cost | Lausch, Ann Kathrin / Cluj PS-SC/ETX | Operation of Service | new | required for serivce delivery, OPS and support / 100% FTE wanted, to be discussed | 100% | 1550 | 148.5 | 230175 | 1550 | 230175 | 54000 | #REF! |  | -176175
OPS Team EU (VI) | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Service Operation EU - VI | PS-SC/PAC Other Costs | Other cost? |  | Operation of Service | new |  | to be aligned with Gernot | #REF! | 148.5 | #VALUE! | #VALUE! | 150000 | 150000 |  |  | #VALUE!
OPS Team NA (VI) | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Service Operation NA - VI | PS-SC/PAC Other Costs | Other cost? |  | Operation of Service | new |  | to be aligned with Gernot | #REF! | 148.5 | #VALUE! | #VALUE! | 150000 | 150000 |  |  | #VALUE!
PjM, Biz Dev, service mng | Rest ögP, equivalent to _007 | BM-00110021_003 | Partner Manager | PS-SC/PAC PAC1 | Personnel cost | Hornung, Floyd? | Partner | constant | required to build and maintane C-Hub partnerships (Antenna, Wire harness, CAN reader, …) | 100% | #REF! | 148.5 | #REF! | #REF! | #REF! | 178000 | 36749 | topics: Kabelbäume, Antennen, ind CAN reader, Sensors TPMS,… | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | EPQ | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Lakshmi, Ramakrishnan | PjM, Release | constant | no C-Hub releases at PS | 35% | #REF! | #REF! | #REF! | #REF! | #REF! | 18000 | #REF! |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Security Manager | MS/ECY-IN_iGPM Developer | Personnel cost | Shashikumar, Nagaraju; Khandelwal, Priti | PjM, Release | constant | no C-Hub updates for new features like Wlan/BLE | 30% | #REF! | #REF! | #REF! | #REF! | #REF! | 20000 | #REF! |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Support BGSW (Arun) | MS/END-IN_iGPM Mechanical_Design_Services_W/O_CAD_SW_PS_Sensors | Personnel cost | Palanisamy, Babu | PjM, Release | constant | required to maintane comlex controlling structure | 50% | #REF! | #REF! | #REF! | #REF! | #REF! | 20000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | Other cost | Marianne, Nina | PjM, Release | constant | no customer documentation, unhappy customers, blocking releases | same as 2025 | #REF! | #REF! | #VALUE! | #VALUE! | 116092 | 116092 | 127254.4946 | Based on BP26 in PLW 71_1947 C-Hub Core Functions | #VALUE!
E2E C-Hub System Team | Rest ögP, equivalent to _007 | BM-00110021_003 | Product development lead | PS-CV/EES System Engineer EES (ex CVO/ENP) | Personnel cost | Hodzic, Alkis -> Transfer Alkis to PS-S -> C reduces costs | PjM, Release | constant | required | 100% | #REF! | 140.3 | #REF! | #REF! | #REF! | 201000 | 248000 | Input Alkis (16-Sep-25): For 2026 it would be ~200.600 € | #REF!
PjM, Biz Dev, service mng | Rest non-ögP, equivalent to _006 | BM-00110021_002 | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | Other cost | Rainer, Stan | PjM, Release | constant | required | other cost | #REF! | #REF! |  | #VALUE! | 355125 | 355125 | 298288.9886 | Based on BP26 in PLW 71_1947 C-Hub Core Functions | 355125
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | BM-00110021_004 | C-Hub XC Series Care_004 | Various XC | Other cost | Multiple | R&D BSW | reduced | no C-Hub support for bugfixing and maintanance; no new features possible |  | #REF! | #REF! | #REF! | #REF! | 626875 | 626875 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | BM-00110021_005 | C-Hub XC Series Care_005 | Various XC | Other cost | Multiple | R&D BSW | reduced | no C-Hub support for bugfixing and maintanance; no new features possible |  | #REF! | #REF! | #REF! | #REF! | 626875 | 626875 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | BM-00110021_004 | C-Hub XC New Features | Various XC | Other cost | Multiple | R&D BSW | reduced | no new features possible |  | #REF! | #REF! | #REF! | #REF! | 110625 | 110625 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | BM-00110021_005 | C-Hub XC New Features | Various XC | Other cost | Multiple | R&D BSW | reduced | no new features possible |  | #REF! | #REF! | #REF! | #REF! | 110625 | 110625 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | CVIT Partner Manager | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | constant | Cojali integration and alignment critical: delays in the delivery of contract, cojali container framework for different vehicles. Mandatory need a person which would build up the relationsship. | 100% | #REF! | #REF! | #REF! | #REF! | 130000 | 130000 | #REF! |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | reduced | RP1210 development and stabilisation stopped. no further support for this library. Premium data failed. |  | #REF! | #REF! | #REF! | #REF! | 150000 | 150000 | #REF! |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | R&D at Cojali | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | reduced | required for premium data | other cost | #REF! | #REF! |  | #VALUE! | 150000 | 150000 | #REF! |  | 150000
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | PO for Cojali | PS-SC/PAC Other Costs | Other cost | Scholz, Sebastian | R&D Cojali | constant | mandatory for Cojali --> possible transfer to PS? |  | #REF! | #REF! | #REF! | #REF! | 150000 | 150000 |  |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | VCS R&D | PS-SC/PAC Other Costs | Other cost | (blank) | R&D for Service | reduced | no Cojali, no premium data, risk for customer acquisitions, no new features |  | #REF! | #REF! | #REF! | #REF! | 975000 | 975000 | #REF! |  | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | BM-00110021_004 | C-Hub XC - HW Change for RS-232, K-LINE |  |  |  | R&D HW | new | no cold chain support and Tacho access ofer D8 port (easier way to get the data) |  | #REF! | #REF! | #REF! | #REF! | 200000 | 200000 |  |  | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | BM-00110021_005 | C-Hub XC - HW Change for RS-232, K-LINE |  |  |  | R&D HW | new | no cold chain support and Tacho access ofer D8 port (easier way to get the data) |  | #REF! | #REF! | #REF! | #REF! | 200000 | 200000 |  |  | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | BM-00110021_002 | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | Other cost | Gibayev Oleg | R&D Service | constant | no container application support for any customer. No Cojali vehicle container creation. No premium data. | 100% | #REF! | #REF! | #REF! | #REF! | 136028.672 | 136028.672 | 184456.5169 | Based on BP26 in PLW 71_1947 C-Hub Core Functions | #REF!
E2E C-Hub System Team | Rest ögP, equivalent to _007 | BM-00110021_003 | CDK development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | tbd | R&D Service | new | required for main customers like Penske, … | 100% | #REF! | 52.5392 | #REF! | #REF! | #REF! | 150000 |  |  | #REF!
Other costs | Rest ögP, equivalent to _007 | BM-00110021_003 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Other cost | (blank) | R&D System | constant |  | other cost | #REF! | #REF! |  | #VALUE! | 50000 | 50000 | #REF! |  | 50000
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Customer Cloud Integration / pre-development for VI integration | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | Modoc, Daniel Stefan | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 60000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | E2E System Team - Requirements Eng. & System development | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Praveen, K M | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… no concept and requirements specification for XC and ETAS | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 54000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | E2E System Team - SysArch - Requirements Eng. & System development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | Guias, Cornel Liviu; Hategan, Liviu Ioan; | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… no concept and requirements specification for XC and ETAS | 200% | #REF! | #REF! | #REF! | #REF! | #REF! | 190000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | System integration and performing V&V | PS-CV/EES System Engineer EES (ex CVO/ENP) | Personnel cost | Blohm, Christina; Frank, Kornelius | R&D System | increased | Christina: Dako Support, allerlei Support HW, Fahrzeug Aufbauten, Fahrzeugtests für den C-Hub release Kornelius: Fahrzeugtests für den C-Hub release | 100% | #REF! | 140.3 | #REF! | #REF! | #REF! | 143571.4286 | #REF! |  | #REF!
E2E C-Hub System Team | Rest ögP, equivalent to _007 | BM-00110021_003 | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | Personnel cost | Perless, Alexander | R&D System | constant | no customer support, no specification of new concepts and requirements, further development of the vehicle database, integration with VI | 100% | #REF! | 148.5 | #REF! | #REF! | #REF! | 163000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Managing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Personnel cost | Fagarasi, Lorand | R&D System | constant | no C-Hub releases at PS | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 92000 | #REF! |  | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BM-00110021_002 | Performing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Personnel cost | Chirlejan, Alex Bogdan | R&D System | constant | no C-Hub releases at PS | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | 92000 | #REF! |  | #REF!
| Rest non-ögP, equivalent to _006 | BM-00110021_002 | Installation App development | PS-SC/PAC Other Costs | Other cost |  | R&D System | new |  |  | #REF! | #REF! | #REF! | #REF! | 150000 | 150000 | #REF! |  | #REF!
Total | [12 empty] | #REF! |  | #REF! | 8991817.1006 | #REF!
Assumptions
Cold chain support mandatory to scale in 2026ff -->RS-232 required
CDK required to support container use-case
Limited feature development in BSW at XC-CP
Releases: v1.4 (02/2026) ASW-only; v1.5 (05/2026) incl. Plant release; v1.6 (10/2026)
Note on K18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FTE to be confirmed
Note on K20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as 2025
Note on R22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For 2026 it would be ~200.600 €
Note on Q35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) is that really the cost for Oleg?

## Final input Arun 002&003 (2) (hidden)
New MCR ID | Task name | Resource group | Orga | Orga new | Cost type | Person booking | Hrs | Amount
BM-00110021_003 | Refunding for C-Hub main project ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding |  |  | Refunding | (blank) |  | -330000
BM-00110021_002 | Customer integrations | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | assumtption: 10 customer á 80k€ |  | 0
BM-00110021_002 | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | Dirk needed for tranfer to PS |  | 202500
BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 1496 | 78598.6667
BM-00110021_002 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Dhingra, Manish | 1871 | 52469
BM-00110021_002 | Data / rev. Eng. and AI | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | (blank) |  | 0
BM-00110021_002 | Series Logistics Concept | PS-SC/PAC Other Costs | M | M | Other cost | (blank) |  | 0
BM-00110021_002 | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | PA-CS/NA | Personnel cost |  | 3720 | 423141.913
BM-00110021_002 | VCS SW maintance | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 370000
BM-00110021_002 | System integration and performing V&V | PS-SC/XPS PS-SC XPS development | PA-CS | PA-CS | Personnel cost | Patrick, has not booked yet. | 721 | 124588.8
BM-00110021_002 | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Sorina + tbd | 2244 | 117898
BM-00110021_002 | Service Management | PS-SC/ETX | Cluj | Cluj | Personnel cost | Lausch, Ann Kathrin / Cluj PS-SC/ETX | 1550 | 81435.7843
BM-00110021_002 | Service Operation EU - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 50000
BM-00110021_002 | Service Operation NA - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 50000
BM-00110021_003 | Partner Manager | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Hornung, Floyd? | 283.8 | 42144.3
BM-00110021_002 | EPQ | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Lakshmi, Ramakrishnan | 654.85 | 18361.994
BM-00110021_002 | Security Manager | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | IN | Personnel cost | Shashikumar, Nagaraju; Khandelwal, Priti | 374 | 19649.6667
BM-00110021_002 | Support BGSW (Arun) | MS/END-IN_iGPM Mechanical_Design_Services_W/O_CAD_SW_PS_Sensors | IN | IN | Personnel cost | Palanisamy, Babu | 936 | 19721.52
BM-00110021_002 | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | BD | BD | Other cost | Marianne, Nina |  | 87000
BM-00110021_003 | Product development lead | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | CV | Personnel cost | Hodzic, Alkis -> Transfer Alkis to PS-S -> C reduces costs | 1617 | 226865.1
BM-00110021_002 | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | BD | BD | Other cost | Rainer, Stan |  | 355125
BM-00110021_002 | CVIT Partner Manager | PS-SC/PAC Other Costs | Bari | Bari | Other cost | (blank) |  | 98689.3394
BM-00110021_002 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | (blank) |  | 80000
BM-00110021_002 | R&D at Cojali | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 90000
BM-00110021_002 | PO for Cojali | PS-SC/PAC Other Costs | VCS | VCS | Other cost | Scholz, Sebastian |  | 180000
BM-00110021_002 | VCS R&D | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 682500
BM-00110021_002 | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | BD | BD | Other cost | Gibayev Oleg |  | 136028.672
BM-00110021_003 | CDK development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 1496 | 78598.6667
BM-00110021_002 | Technical Docu Cluj | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | tbd | 748 | 39299.3333
BM-00110021_003 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 20000
BM-00110021_002 | Customer Cloud Integration / pre-development for VI integration | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Modoc, Daniel Stefan | 1496 | 78598.6667
BM-00110021_002 | E2E System Team - Requirements Eng. & System development | MS/ECP-PS-IN_iGPM SW-Services_DP | IN | IN | Personnel cost | Praveen, K M | 1871 | 52462.84
BM-00110021_002 | E2E System Team - SysArch - Requirements Eng. & System development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Guias, Cornel Liviu; Hategan, Liviu Ioan; | 2992 | 157197.3333
BM-00110021_002 | System integration and performing V&V | PS-CV/EES System Engineer EES (ex CVO/ENP) | CV | CV | Personnel cost | Blohm, Christina; Frank, Kornelius | 511.6587 | 71785.7143
BM-00110021_003 | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Perless, Alexander | 1419 | 210721.5
BM-00110021_002 | Managing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Cluj | Personnel cost | Fagarasi, Lorand | 1550 | 81437
BM-00110021_002 | Performing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Cluj | Cluj | Personnel cost | Chirlejan, Alex Bogdan | 1550 | 81437
BM-00110021_002 | Installation App development | PS-SC/PAC Other Costs | Operation | Operation | Other cost |  |  | 0
C-Hub Cust Ext - Rainer to define MCR | Customer integrations | PS-SC/PAC Other Costs | PA-CS | PA-CS | Other cost | assumtption: 10 customer á 80k€ |  | 200000
C-Hub Cust Ext - Rainer to define MCR | MA for vehicle configuration | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | Dirk needed for tranfer to PS |  | 67500
C-Hub Cust Ext - Rainer to define MCR | NA Team + other cost | PS-SC/EBR-NA SW Eng | PA-CS/NA | PA-CS/NA | Personnel cost |  | 3720 | 423141.913
C-Hub Cust Ext - Rainer to define MCR | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Cluj | Cluj | Personnel cost | Sorina + Bianca + Maria (200%) | 2244 | 78598.6667
C-Hub Cust Ext - Rainer to define MCR | Service Operation EU - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 75000
C-Hub Cust Ext - Rainer to define MCR | Service Operation NA - VI | PS-SC/PAC Other Costs | Operation | Operation | Other cost? |  |  | 75000
C-Hub Cust Ext - Rainer to define MCR | Partner Manager | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Hornung, Floyd? | 283.8 | 42144.3
C-Hub Cust Ext - Rainer to define MCR | C-Hub XC New Features | Various XC | XC | XC | Other cost | Multiple |  | 286993.92
C-Hub Cust Ext - Rainer to define MCR | ETAS-MSS Cojali | PS-SC/PAC Other Costs | ETAS | ETAS | Other cost | (blank) |  | 70000
C-Hub Cust Ext - Rainer to define MCR | R&D at Cojali | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 270000
C-Hub Cust Ext - Rainer to define MCR | VCS R&D | PS-SC/PAC Other Costs | VCS | VCS | Other cost | (blank) |  | 292500
C-Hub Cust Ext - Rainer to define MCR | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Operation | Operation | Other cost | (blank) |  | 30000
C-Hub Cust Ext - Rainer to define MCR | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | PA-CS | PA-CS | Personnel cost | Perless, Alexander | 1419 | 42144.3
248329.5667
248.3296
|  |  | PDCL | M Euro | % Of PDCL | M Euro
| 5492624.6504 |  | P00540 | 5.4926 | 49% | 2.6914
| 5492624.6504 |  | P00280 | 5.4926 | 51% | 2.8012
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hodzic Alkis (PS-CV/EES PS-SC/XPS) macht es Sinn die Aufgaben von Manish nach Cluj zu transferieren? Reply: JA wie besprochen.
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be transfered to Cluj M2026
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP)
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) resource group changed --> now Cluj Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from Germany to Cluj and 007 to 006 (no ögP) Reply: @Karaivanov Stanislav (BD/SPB-APA9) changed from India to Cluj

## Draft_Arun (hidden)
Team bucket | New MCR logic | Task name | Resource group | Cost type | Person booking | new Team | delta to 2025 | consequence if canceled | FTE (%) 2026 | Hrs 2026 | Rate 2026 | Personnel costs | Prognosis BP26 | Prognosis BP27 | C-Hub CF09/2025 (before redistribution to Cust. Proj) | Comments to Prognosis BP26
Refunding | Rest ögP, equivalent to _007 | Refunding for C-Hub main project ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding | Refunding | (blank) | - |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
Refunding | XC ögP, equivalent to_005 | Refunding for C-Hub XC ögP | PS-SC/CE-EU, CE-PE Publicly Funded Project - Refunding | Refunding | (blank) | - |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
Customer specific effort | Rest non-ögP, equivalent to _006 | Customer integrations | PS-SC/PAC Other Costs | Other cost | assumtption: 10 customer á 80k€ | Customer specific | new |  |  | #REF! | #REF! | #REF! | 800000 | 800
Cojali Development | Rest non-ögP, equivalent to _006 | MA for vehicle configuration | PS-SC/PAC Other Costs | Other cost | Dirk needed for tranfer to PS | DaaS Delivery | constant | special know how for RD. No other person available. Lead: no standard diagnostics data or RD use cases like for TOP107, Austria, ECP | 100% | #REF! | #REF! | #REF! | 270000 | 270 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Transfer to PS (Vienna?) | DaaS Delivery | new | no transfer to PS possible | 100% | #REF! | #REF! | #REF! | 150000 | 150
Cojali Development | Rest non-ögP, equivalent to _006 | RM+RD config + Cojali + Pantaris configs | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Dhingra, Manish | DaaS Delivery | constant | no RM configs (CAN Data) for any use-case / required for DaaS | 100% | #REF! | #REF! | #REF! | 54000 | 54 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | Data / rev. Eng. and AI | PS-SC/PAC Other Costs | Other cost | (blank) | DaaS Delivery | new | LCV data not available; no support of EVs; support busses difficult | other cost | #REF! | #REF! |  | 150000 | 150 | #REF!
Other costs | Rest non-ögP, equivalent to _006 | Series Logistics Concept | PS-SC/PAC Other Costs | Other cost | (blank) | Logistics | constant | no delivery to new customers possible; no handling of shortage etc. | other cost | #REF! | #REF! |  | 67000 | 67 | #REF!
NA Activities | Rest non-ögP, equivalent to _006 | NA Team + other cost | PS-EC EBR-NA SW Eng | Personnel cost |  | NA Localization | increasing | no NA customer acquisition support and no NA C-Hub. | pauschal top-down geschätzt | #REF! | #REF! | #VALUE! | 790000 | 790
Cojali Development | Rest non-ögP, equivalent to _006 | VCS SW maintance | PS-SC/PAC Other Costs | Other cost | (blank) | Operation of Service | constant | stop C-Hub | Walter/Rainer klärt mit Daniel | #REF! | #REF! | #VALUE! | 400000 | 400 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | System integration and performing V&V | PS-SC/XPS PS-SC XPS development | Personnel cost | Patrick, has not booked yet. | Operation of Service | constant | no customer support ww; E2E integration, testing, and release; no Remodul tech support | 100% | #REF! | #REF! | #REF! | 160000 | 160
PjM, Biz Dev, service mng | Rest ögP, equivalent to _007 | Operations L1/L2 Incident/Problem/Monitoring | PS-SC/PAC PAC1 | Personnel cost | Beck, Jochen --> transfer to Cluj | Operation of Service | constant | required for serivce delivery, OPS and support | 100% | #REF! | #REF! | #REF! | 178000 | 178 | #REF!
PjM, Biz Dev, service mng | Rest non-ögP, equivalent to _006 | Service Management | PS-SC/ETX | Personnel cost | Lausch, Ann Kathrin / Cluj PS-SC/ETX | Operation of Service | new | required for serivce delivery, OPS and support / 100% FTE wanted, to be discussed | 100% | 1550 | 52.5392 | 81435.7843 | 54000 | 54 | #REF!
OPS Team EU (VI) | Rest non-ögP, equivalent to _006 | Service Operation EU - VI | PS-SC/PAC Other Costs | Other cost? |  | Operation of Service | new |  | to be aligned with Gernot | #REF! | #REF! | #VALUE! | 150000 | 150
OPS Team NA (VI) | Rest non-ögP, equivalent to _006 | Service Operation NA - VI | PS-SC/PAC Other Costs | Other cost? |  | Operation of Service | new |  | to be aligned with Gernot | #REF! | #REF! | #VALUE! | 150000 | 150
PjM, Biz Dev, service mng | Rest ögP, equivalent to _007 | Partner Manager | PS-SC/PAC PAC1 | Personnel cost | Hornung, Floyd? | Partner | constant | required to build and maintane C-Hub partnerships (Antenna, Wire harness, CAN reader, …) | 100% | #REF! | #REF! | #REF! | 178000 | 178 | 36749 | topics: Kabelbäume, Antennen, ind CAN reader, Sensors TPMS,…
Cojali Development | Rest non-ögP, equivalent to _006 | EPQ | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Lakshmi, Ramakrishnan | PjM, Release | constant | no C-Hub releases at PS | 35% | #REF! | #REF! | #REF! | 18000 | 18 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | Security Manager | MS/ECY-IN_iGPM Developer | Personnel cost | Shashikumar, Nagaraju; Khandelwal, Priti | PjM, Release | constant | no C-Hub updates for new features like Wlan/BLE | 30% | #REF! | #REF! | #REF! | 20000 | 20 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | Support BGSW (Arun) | MS/END-IN_iGPM Mechanical_Design_Services_W/O_CAD_SW_PS_Sensors | Personnel cost | Palanisamy, Babu | PjM, Release | constant | required to maintane comlex controlling structure | 50% | #REF! | #REF! | #REF! | 20000 | 20 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | BD Support (Technical Documentation) | PS-SC/PAC Other Costs | Other cost | Marianne, Nina | PjM, Release | constant | no customer documentation, unhappy customers, blocking releases | same as 2025 | #REF! | #REF! | #VALUE! | 116092 | 116.092 | 127254.4946 | Based on BP26 in PLW 71_1947 C-Hub Core Functions
E2E C-Hub System Team | Rest ögP, equivalent to _007 | Product development lead | PS-CV/EES System Engineer EES (ex CVO/ENP) | Personnel cost | Hodzic, Alkis -> Transfer Alkis to PS-S -> C reduces costs | PjM, Release | constant | required | 100% | #REF! | #REF! | #REF! | 201000 | 201 | 248000 | Input Alkis (16-Sep-25): For 2026 it would be ~200.600 €
PjM, Biz Dev, service mng | Rest non-ögP, equivalent to _006 | BD Support (PjM and Controlling) | PS-SC/PAC Other Costs | Other cost | Rainer, Stan | PjM, Release | constant | required | other cost | #REF! | #REF! |  | 355125 | 355.125 | 298288.9886 | Based on BP26 in PLW 71_1947 C-Hub Core Functions
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | C-Hub XC Series Care_004 | Various XC | Other cost | Multiple | R&D BSW | reduced | no C-Hub support for bugfixing and maintanance; no new features possible |  | #REF! | #REF! | #REF! | 626875 | 626.875 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | C-Hub XC Series Care_005 | Various XC | Other cost | Multiple | R&D BSW | reduced | no C-Hub support for bugfixing and maintanance; no new features possible |  | #REF! | #REF! | #REF! | 626875 | 626.875 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | C-Hub XC New Features | Various XC | Other cost | Multiple | R&D BSW | reduced | no new features possible |  | #REF! | #REF! | #REF! | 110625 | 110.625 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | C-Hub XC New Features | Various XC | Other cost | Multiple | R&D BSW | reduced | no new features possible |  | #REF! | #REF! | #REF! | 110625 | 110.625 | #REF! | BP26 -> mail from Oezcan Can, 22-Jul: [C-Hub_XC] CF09/25 & BP26 : Update MCR projects
Cojali Development | Rest non-ögP, equivalent to _006 | CVIT Partner Manager | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | constant | Cojali integration and alignment critical: delays in the delivery of contract, cojali container framework for different vehicles. Mandatory need a person which would build up the relationsship. | 100% | #REF! | #REF! | #REF! | 130000 | 130 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | ETAS-MSS Cojali | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | reduced | RP1210 development and stabilisation stopped. no further support for this library. Premium data failed. |  | #REF! | #REF! | #REF! | 150000 | 150 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | R&D at Cojali | PS-SC/PAC Other Costs | Other cost | (blank) | R&D Cojali | reduced | required for premium data | other cost | #REF! | #REF! |  | 150000 | 150 | #REF!
Cojali Development | Rest non-ögP, equivalent to _006 | PO for Cojali | PS-SC/PAC Other Costs | Other cost | Scholz, Sebastian | R&D Cojali | constant | mandatory for Cojali --> possible transfer to PS? |  | #REF! | #REF! | #REF! | 150000 | 150
Cojali Development | Rest non-ögP, equivalent to _006 | VCS R&D | PS-SC/PAC Other Costs | Other cost | (blank) | R&D for Service | reduced | no Cojali, no premium data, risk for customer acquisitions, no new features |  | #REF! | #REF! | #REF! | 975000 | 975 | #REF!
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _004 | C-Hub XC - HW Change for RS-232, K-LINE |  |  |  | R&D HW | new | no cold chain support and Tacho access ofer D8 port (easier way to get the data) |  | #REF! | #REF! | #REF! | 200000 | 200
XC-CP | XC, split 50/50 ögp/non-ögp, equivalent to _005 | C-Hub XC - HW Change for RS-232, K-LINE |  |  |  | R&D HW | new | no cold chain support and Tacho access ofer D8 port (easier way to get the data) |  | #REF! | #REF! | #REF! | 200000 | 200
Cojali Development | Rest non-ögP, equivalent to _006 | BD Support (Cojali & CDK) | PS-SC/PAC Other Costs | Other cost | Gibayev Oleg | R&D Service | constant | no container application support for any customer. No Cojali vehicle container creation. No premium data. | 100% | #REF! | #REF! | #REF! | 136028.672 | 136.0287 | 184456.5169 | Based on BP26 in PLW 71_1947 C-Hub Core Functions
E2E C-Hub System Team | Rest ögP, equivalent to _007 | CDK development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | tbd | R&D Service | new | required for main customers like Penske, … | 100% | #REF! | #REF! | #REF! | 150000 | 150
Other costs | Rest ögP, equivalent to _007 | Other cost / Lab, HW etc. | PS-SC/PAC Other Costs | Other cost | (blank) | R&D System | constant |  | other cost | #REF! | #REF! |  | 50000 | 50 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | Customer Cloud Integration / pre-development for VI integration | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | Modoc, Daniel Stefan | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… | 100% | #REF! | #REF! | #REF! | 60000 | 60 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | E2E System Team - Requirements Eng. & System development | MS/ECP-PS-IN_iGPM SW-Services_DP | Personnel cost | Praveen, K M | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… no concept and requirements specification for XC and ETAS | 100% | #REF! | #REF! | #REF! | 54000 | 54 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | E2E System Team - SysArch - Requirements Eng. & System development | PS-SC/EDS_PS-SC EDS_PS-SC_XPS | Personnel cost | Guias, Cornel Liviu; Hategan, Liviu Ioan; | R&D System | constant | no integration with external cloud solutions for PoC's, pilots and series like geoTab,… no concept and requirements specification for XC and ETAS | 200% | #REF! | #REF! | #REF! | 190000 | 190 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | System integration and performing V&V | PS-CV/EES System Engineer EES (ex CVO/ENP) | Personnel cost | Blohm, Christina; Frank, Kornelius | R&D System | increased | Christina: Dako Support, allerlei Support HW, Fahrzeug Aufbauten, Fahrzeugtests für den C-Hub release Kornelius: Fahrzeugtests für den C-Hub release | 100% | #REF! | #REF! | #REF! | 143571.4286 | 143.5714 | #REF!
E2E C-Hub System Team | Rest ögP, equivalent to _007 | System Integration and Solution Architecture technical customer support | PS-SC/PAC PAC1 | Personnel cost | Perless, Alexander | R&D System | constant | no customer support, no specification of new concepts and requirements, further development of the vehicle database, integration with VI | 100% | #REF! | #REF! | #REF! | 163000 | 163 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | Managing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Personnel cost | Fagarasi, Lorand | R&D System | constant | no C-Hub releases at PS | 100% | #REF! | #REF! | #REF! | 92000 | 92 | #REF!
E2E C-Hub System Team | Rest non-ögP, equivalent to _006 | Performing V&V | PS-SC/ETX V&V CE Other Cust. Proj. | Personnel cost | Chirlejan, Alex Bogdan | R&D System | constant | no C-Hub releases at PS | 100% | #REF! | #REF! | #REF! | 92000 | 92 | #REF!
| Rest non-ögP, equivalent to _006 | Installation App development | PS-SC/PAC Other Costs | Other cost |  | R&D System | new |  |  | #REF! | #REF! | #REF! | 150000 | 150 | #REF!
Total | [12 empty] | 920000 |  | #REF!
Assumptions
Cold chain support mandatory to scale in 2026ff -->RS-232 required
CDK required to support container use-case
Limited feature development in BSW at XC-CP
Releases: v1.4 (02/2026) ASW-only; v1.5 (05/2026) incl. Plant release; v1.6 (10/2026)
Note on J18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FTE to be confirmed
Note on J20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as 2025
Note on P22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For 2026 it would be ~200.600 €
Note on N35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Karaivanov Stanislav (BD/SPB-APA9) is that really the cost for Oleg?